## Supplier Scorecard
Goodada Supplier Information Reliability Scorecard
Assess how much confidence your supply plan should place in information received from each supplier.
Supplier name
Assessment date
Assessed by
Order / product
# | Assessment area | Score (1-5) | Weight | Weighted score | Evidence / comments | Risk flag | Recommended action
1 | Production status accuracy |  | 1 | 0 | Does reported progress consistently match verified reality?
2 | Delivery date reliability |  | 1 | 0 | Does the supplier consistently achieve confirmed completion/shipment dates?
3 | Early warning of delays |  | 1 | 0 | Does the supplier proactively report risks before dates are affected?
4 | Evidence supporting progress |  | 1 | 0 | Are progress claims supported by quantities, dates, photos or records?
5 | Raw-material visibility |  | 1 | 0 | Does the supplier clearly report material availability, shortages and arrivals?
6 | Quality issue transparency |  | 1 | 0 | Are quality issues and corrective actions reported early and clearly?
7 | Production capacity reliability |  | 1 | 0 | Does demonstrated capacity consistently support commitments?
8 | Subcontracting transparency |  | 1 | 0 | Is subcontracted production/process risk fully disclosed?
9 | Packing / shipment readiness accuracy |  | 1 | 0 | Do 'ready' dates match finished, approved and packed quantities?
10 | Promise vs actual performance |  | 1 | 0 | Do historical commitments closely match actual outcomes?
Overall score | 0
Maximum score | 50
Information confidence | Low confidence
Management response | Consider stronger independent oversight and earlier verification
Important: This score measures information reliability for planning decisions. It does not replace product quality controls, supplier audits or commercial due diligence.

## Performance History
Supplier Performance & Confidence Gap History
Use actual order data to compare supplier commitments with verified outcomes over time.
Supplier | Order / PO | Milestone / metric | Promised date | Actual / verified date | Days variance | Promised % | Verified % | Percentage-point gap | Evidence / notes | Planning implication

## Scoring Guide
Scoring Guide
Assessment area | 1 – Low confidence | 3 – Moderate | 5 – High confidence | What to look for
Production status accuracy | Reported progress frequently differs from reality | Generally accurate with some discrepancies | Reported progress consistently matches actual status | Compare supplier reports with verified quantities/stages
Delivery date reliability | Frequently misses confirmed dates | Occasional delays | Consistently achieves confirmed dates | Compare promised vs actual completion/shipment dates
Early warning of delays | Problems disclosed very late | Usually provides some warning | Proactively reports risks before dates are affected | Record when risks were first communicated
Evidence supporting progress | Statements with little evidence | Some photos/data supplied | Clear quantities, dates and supporting evidence | Request objective evidence for critical milestones
Raw-material visibility | Material status unclear | Basic updates available | Clear availability, shortage and arrival reporting | Check material status before production commitments
Quality issue transparency | Problems generally emerge late | Major issues normally communicated | Issues and corrective actions proactively reported | Track disclosure timing and corrective actions
Production capacity reliability | Commitments frequently exceed capability | Generally capable with occasional constraints | Capacity consistently supports commitments | Compare capacity claims with actual output
Subcontracting transparency | Little visibility | Disclosed when asked | Full visibility of subcontracted processes/risks | Identify external processes and controls
Packing / shipment readiness accuracy | Ready dates frequently unreliable | Usually reasonably accurate | Finished, approved and packed quantities clearly reported | Define 'ready' precisely
Promise vs actual performance | Significant recurring differences | Some differences | Commitments closely match actual outcomes | Use historical variance data
Score | Information confidence | Suggested management response
41–50 | Higher confidence | Routine monitoring may be sufficient
31–40 | Reasonable confidence | Verify important milestones on higher-risk orders
21–30 | Limited confidence | Consider regular production verification
10–20 | Low confidence | Consider stronger independent oversight and earlier verification